PROJECT PLAN and Management

# Intelligent Infrastructure Automation Platform

Prepared for technology leadership, platform engineering, security, and operations stakeholders

# Executive Summary

The Intelligent Infrastructure Automation Platform will provide a governed self service path from a Git repository to a running Kubernetes workload. The platform standardizes repository onboarding, infrastructure provisioning, continuous integration, deployment, observability, and access control across engineering teams. Terraform manages infrastructure as code, Ansible automates configuration, Jenkins orchestrates pipelines, and Kubernetes runs workloads.

The recommended approach is a staged rollout. The MVP proves a secure path for one cloud landing zone and a limited group of teams. Enhancements add policy, templates, approvals, and broader integrations. The final phase hardens the service for production scale through high availability, auditability, reliability engineering, and operating-model maturity.

## Decision Requested

Approve Phase 1 discovery and MVP delivery, nominate accountable business and technical owners, and authorize the core team to validate target cloud, identity, and Git hosting integrations before implementation begins.

# Objectives

Reduce the elapsed time from repository onboarding to a compliant non production deployment.

Provide repeatable infrastructure and application delivery patterns that reduce manual configuration.

Embed security, access control, policy checks, and deployment traceability in the delivery path.

Give teams a clear operational view of project health, deployments, and automated remediation signals.

# Success Criteria

| Outcome | Phase 1 target | Measurement |
| --- | --- | --- |
| Onboarding speed | A new approved repository can reach dev in under 60 minutes | Median onboarding to first deploy time |
| Deployment reliability | At least 90 percent successful automated deployments | Successful deployments / total deployments |
| Policy adoption | All onboarded projects use approved templates | Template compliance audit |
| User value | At least 5 pilot teams actively deploy through the platform | Monthly active delivery teams |

# Scope

## In Scope

GitHub or approved Git provider connection, repository selection, and branch-based deployment triggers.

Reusable application templates, Docker image build, artifact storage, and Jenkins pipeline execution.

Terraform managed cloud and Kubernetes prerequisites for approved environments.

Kubernetes deployment, health checks, rollout status, logs, and basic rollback capability.

Role based access, audit events, secrets integration, dashboards, and operational reporting.

## Out of Scope for Initial MVP

Migration of every legacy application or replacement of existing enterprise ITSM processes.

Multi cloud parity, advanced FinOps optimization, and bespoke delivery support for every technology stack.

Production deployments without required security, change, and operational approvals.

# Stakeholders

| Stakeholder group | Primary interest | Engagement |
| --- | --- | --- |
| Executive sponsor | Business value, risk, funding, adoption | Monthly steering committee |
| Platform engineering | Architecture, delivery, reliability | Weekly delivery review |
| Application teams | Simple onboarding and dependable releases | Pilot feedback and demos |
| Security and compliance | Identity, secrets, policy, audit evidence | Design gates and controls review |
| Operations and SRE | Service support, observability, incident response | Operational readiness review |
| Finance and procurement | Cloud cost, vendors, licensing | Stage gate and quarterly review |

# Governance

Governance uses lightweight decision forums that protect delivery speed while preserving clear accountability.

| Forum | Cadence | Purpose | Decision owner |
| --- | --- | --- | --- |
| Steering committee | Monthly | Funding, scope, risk escalation, stage approval | Executive sponsor |
| Architecture review | Biweekly | Standards, integration choices, exceptions | Chief architect |
| Delivery review | Weekly | Milestones, blockers, dependencies, quality | Platform lead |
| Change advisory review | As needed | Production impacting changes | Operations lead |

# High Level System Architecture

The architecture separates the developer experience from the automation control plane and runtime environments. Each layer has explicit identity, audit, and policy controls.

| Layer | Core components | Responsibilities |
| --- | --- | --- |
| Developer portal | Web UI, API, project catalog, deployment view | Repository onboarding, configuration, status, approvals, self service |
| Identity and policy | SSO, RBAC, secrets manager, policy engine | Authentication, authorization, secret retrieval, guardrails, audit |
| Automation control plane | Jenkins, Terraform, Ansible, artifact registry | Build, plan, provision, configure, promote, retain evidence |
| Runtime platform | Kubernetes clusters, ingress, monitoring, logging | Run workloads, expose services, observe health, support rollback |
| Integration layer | Git provider, cloud APIs, ITSM, notifications | Events, source control, infrastructure APIs, change records, alerts |

## Reference Delivery Flow

A developer connects an approved repository and selects a deployment template.

The platform validates ownership, branch rules, secrets, policy, and target environment.

Jenkins builds the workload and publishes a versioned image to the approved registry.

Terraform and Ansible reconcile environment prerequisites and configuration where required.

Kubernetes deploys the image, runs health checks, and reports rollout status to the portal.

The platform records deployment evidence, logs, approvals, and links for audit and support.

# Key Technical Considerations

| Area | Planning requirement |
| --- | --- |
| Identity | Use enterprise SSO, least privilege RBAC, and short lived credentials. Separate human and workload identities. |
| Secrets | Store secrets in an approved vault. Do not persist plaintext secrets in repository, pipeline logs, or portal data. |
| Templates | Version templates and define a supported technology matrix. Provide an exception process for non standard stacks. |
| Policy | Apply policy as code before infrastructure changes and before production deployment. Surface actionable errors to users. |
| Observability | Collect pipeline, application, cluster, and infrastructure signals with correlation IDs and retention rules. |
| Reliability | Use idempotent automation, rollback paths, retry controls, backups, and documented recovery procedures. |

# Milestones and Phased Timeline

Estimates assume a dedicated core team, timely access to cloud and identity platforms, and a limited pilot scope. Calendar duration may change if those dependencies are delayed.

| Phase | Indicative effort | Key deliverables | Exit decision |
| --- | --- | --- | --- |
| Phase 1 MVP | 12 to 16 weeks | Portal foundation, Git connection, one template, CI CD path, dev environment, pilot dashboards | Pilot teams can onboard and deploy a supported service |
| Phase 2 Enhancements | 16 to 20 weeks | Multiple templates, staging and production flow, approvals, policy, secrets, richer observability | Governed production pilots meet reliability targets |
| Phase 3 Prod scale | 20 to 28 weeks | High availability, multi team scale, service operations, audit reporting, performance and resilience hardening | Service is ready for broad organizational adoption |

## Milestone Plan

| Milestone | Target timing | Acceptance evidence |
| --- | --- | --- |
| Initiation and discovery | Weeks 1 to 2 | Approved charter, target users, dependency map, initial architecture |
| MVP design baseline | Weeks 3 to 4 | Backlog, UX flow, security design, pilot repository selection |
| MVP build and integration | Weeks 5 to 11 | End to end development deployment in a non production cluster |
| Pilot validation | Weeks 12 to 14 | Pilot feedback, test evidence, documented support handover |
| MVP stage review | Weeks 15 to 16 | KPI review and approval to fund enhancements |

# Resources and Budget

Budget should be refined after discovery. The following planning view distinguishes the core delivery capacity from operating costs.

| Category | Indicative allocation | Budget planning note |
| --- | --- | --- |
| Core delivery team | 6 to 8 FTE during MVP | Platform lead, product owner, DevOps engineers, frontend or backend engineer, security architect, QA |
| Specialist support | 1 to 2 part time FTE | Cloud, network, identity, compliance, and SRE support as required |
| Cloud and platform services | Variable | Cluster capacity, registry, logging, monitoring, secret management, network services |
| Tooling and licenses | Variable | CI CD, scanning, artifact, observability, and support tooling after enterprise agreements are confirmed |
| Contingency | 10 to 15 percent | Covers integration uncertainty, pilot findings, and security remediation |

# Roles and Responsibilities Matrix

R = Responsible, A = Accountable, C = Consulted, I = Informed. One accountable role is identified for each core decision area.

| Activity | Sponsor | Product owner | Platform lead | Security | SRE Ops | App team |
| --- | --- | --- | --- | --- | --- | --- |
| Business case and funding | A | R | C | I | I | I |
| Roadmap and backlog | I | A/R | C | C | C | C |
| Architecture and standards | I | C | A/R | C | C | I |
| Platform implementation | I | C | A/R | C | C | C |
| Security controls and exceptions | I | C | R | A | C | I |
| Operational readiness | I | C | R | C | A | C |
| Pilot adoption and feedback | I | A | R | I | C | R |
| Production release approval | I | C | R | C | A | I |

## Core Team Roles

| Role | Core responsibility |
| --- | --- |
| Executive sponsor | Owns business outcome, funding, prioritization, and executive escalations. |
| Product owner | Owns user outcomes, backlog priority, acceptance criteria, and stakeholder feedback. |
| Platform engineering lead | Owns technical delivery, architecture alignment, engineering quality, and dependencies. |
| DevOps automation engineer | Builds templates, pipelines, infrastructure modules, integrations, and deployment workflow. |
| Security architect | Defines control requirements, reviews designs, approves exceptions, and supports evidence collection. |
| SRE operations lead | Defines operational model, observability, incident response, reliability targets, and service handover. |

# Risk Management

Risks are reviewed weekly by the delivery team and escalated to the steering committee when they affect scope, funding, target dates, security posture, or pilot viability.

| ID | Risk | Likelihood | Impact | Mitigation and owner |
| --- | --- | --- | --- | --- |
| R1 | Cloud, identity, or network access is delayed | Medium | High | Confirm prerequisites in Weeks 1 to 2; track dependency owners; use a sandbox where possible. Owner: Platform lead |
| R2 | Pilot scope grows beyond supported templates | High | Medium | Publish MVP support boundary; route exceptions to a backlog and architecture review. Owner: Product owner |
| R3 | Secrets or permissions are handled inconsistently | Medium | High | Use approved vault integration, RBAC baseline, audit review, and security sign off before pilots. Owner: Security architect |
| R4 | Automation failures reduce user trust | Medium | High | Implement visible status, actionable errors, retries, rollback, and pilot support coverage. Owner: SRE lead |
| R5 | Unplanned cloud or observability costs | Medium | Medium | Set budget alerts, retention controls, tagging, and monthly cost review. Owner: Finance partner |
| R6 | Low adoption due to workflow mismatch | Medium | High | Co-design with pilot teams, measure task completion, and prioritize high friction improvements. Owner: Product owner |

# KPIs and Reporting

| KPI | Definition | Target by end of Phase 2 | Owner |
| --- | --- | --- | --- |
| Lead time to deploy | Time from approved merge to successful environment deployment | Median under 30 minutes for supported services | Platform lead |
| Deployment success rate | Successful completed deployments divided by total completed deployments | At least 95 percent | SRE lead |
| Onboarding completion | Approved repositories onboarded without manual platform intervention | At least 80 percent | Product owner |
| Policy compliance | Projects passing mandatory controls before promotion | 100 percent | Security architect |
| Pilot satisfaction | Pilot user satisfaction with onboarding and deployment workflow | At least 4.0 / 5 | Product owner |

# Quality Assurance

Define acceptance criteria for every user story, integration, and platform template.

Run unit, integration, security, infrastructure, and end to end deployment tests in the delivery pipeline.

Use peer review for code, infrastructure modules, pipeline definitions, and security sensitive changes.

Maintain release readiness checks for observability, rollback, support documentation, and known risk review.

Validate pilot outcomes with actual application teams before expanding the supported service catalogue.

# Communication Plan

| Audience | Information | Cadence | Channel and owner |
| --- | --- | --- | --- |
| Steering committee | Status, decisions, budget, top risks | Monthly | Decision pack - Executive sponsor |
| Core delivery team | Progress, blockers, next sprint priorities | Weekly | Delivery review - Platform lead |
| Pilot teams | Release notes, known issues, onboarding feedback | Biweekly | Demo and feedback session - Product owner |
| Security and operations | Controls, readiness, incidents, exceptions | At gates and as needed | Review forum - Security and SRE leads |

# Change Control

A requester records the change, rationale, scope effect, urgency, and affected environments.

The product owner and platform lead assess user value, effort, risk, security impact, and timeline effect.

Changes within the agreed delivery tolerance are prioritized through the backlog. Material scope, budget, or schedule changes require steering approval.

Approved changes are documented, scheduled, tested, communicated, and linked to release evidence.

# Exit and Closeout

Confirm agreed deliverables, acceptance evidence, operational ownership, and outstanding known issues.

Complete handover of runbooks, architecture records, support model, access procedures, and cost ownership.

Measure final KPIs against targets and document lessons learned with the pilot teams.

Obtain sponsor acknowledgement of phase completion and approve the next phase, transition, or closure decision.

# Assumptions and Dependencies

| Area | Assumption or dependency | Validation action |
| --- | --- | --- |
| Cloud platform | An approved landing zone and Kubernetes environment are available for the pilot. | Confirm account, network, cluster, and quota readiness during discovery. |
| Git provider | The organization can authorize a GitHub App or OAuth integration with least privilege repository access. | Agree scopes, ownership, and support process with source-control administrators. |
| Identity | Enterprise SSO and group based access are available for the portal and automation services. | Validate identity flow, role mapping, and break glass approach. |
| Security tooling | Secrets, scanning, logging, and audit tooling can be integrated into the target path. | Complete control mapping and a pilot design review. |
| Pilot teams | Pilot teams can provide representative repositories and timely feedback. | Nominate teams and agree pilot success measures before build starts. |